## 12-month checklist
Months before | When | Task | Category | Done
12 | 12 months out | Set your total budget | general
12 | 12 months out | Draft a rough guest count | general
12 | 12 months out | Start researching venues | venue
11 | 11 months out | Shortlist and tour your favorite venues | venue
11 | 11 months out | Plan an engagement shoot | photography
10 | 10 months out | Book your venue | venue
10 | 10 months out | Start the dress / suit search | attire dress
10 | 10 months out | Book your photographer | photography
9 | 9 months out | Book your band or DJ | music band
9 | 9 months out | Book your caterer (if separate from venue) | catering
9 | 9 months out | Start building the guest list | general
8 | 8 months out | Book your florist | flowers
8 | 8 months out | Book hair & makeup trials | hair makeup
8 | 8 months out | Design your save-the-dates | stationery
7 | 7 months out | Send save-the-dates | stationery
7 | 7 months out | Book your officiant | officiant
7 | 7 months out | Set up your registry | general
6 | 6 months out | Order the dress / suit | attire dress
6 | 6 months out | Arrange transport for the day | transport
6 | 6 months out | Reserve hotel blocks for guests | general
5 | 5 months out | Design your invitations | stationery
5 | 5 months out | Plan the honeymoon | general
4 | 4 months out | Send invitations | stationery
4 | 4 months out | Book a cake tasting and order the cake | cake
4 | 4 months out | Order wedding rings | general
3 | 3 months out | Finalize the menu | catering
3 | 3 months out | Schedule dress / suit fittings | attire dress
3 | 3 months out | Build the playlist and do-not-play list | music band
2 | 2 months out | Chase outstanding RSVPs | general
2 | 2 months out | Draft the seating chart | general
2 | 2 months out | Draft vows and speeches | speeches
2 | 2 months out | Confirm details with every vendor | general
1 | 1 month out | Final dress / suit fitting | attire dress
1 | 1 month out | Send the day-of timeline to vendors | general
1 | 1 month out | Print place cards and final stationery | stationery
0 | The week of | Make final vendor payments | general
0 | The week of | Rehearse the ceremony | general
0 | The week of | Pack a day-of emergency kit | general

## Elopement (6 months)
Months before | When | Task | Category | Done
6 | 6 months out | Set your budget | general
6 | 6 months out | Choose your location / venue | venue
5 | 5 months out | Check marriage license requirements for the location | general
4 | 4 months out | Book your officiant | officiant
4 | 4 months out | Book a photographer | photography
3 | 3 months out | Choose your outfits | attire dress
2 | 2 months out | Plan announcements or a celebration party | stationery
1 | 1 month out | Write your vows | speeches
1 | 1 month out | Confirm travel and day-of logistics | general
0 | The week of | Get the marriage license | general